## Slide 1
RFID Implementation Step by Step
Most RFID projects that fail do so because of planning, process and integration gaps, not because the radio technology does not work. This chapter gives a proven nine-step method from objectives to continuous improvement, with...
Indian RFID - Mindware, New Delhi | From consultation to implementation
www.indianrfid.com/rfid-academy/rfid-implementation-guide | +91-9717122688 | gm@indianbarcode.com
MINDWARE

## Slide 2
Why a method matters
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• An RFID system is not a product you switch on; it is a combination of tags, readers, antennas, software, data and changed working practices. Each element can be right on its own while the whole still fails, for example perfect hardware feeding data that no...
MINDWARE

## Slide 3
Steps 1-3: Plan
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• Step 1 - Define objectives and KPIs
• Write down what the business wants to achieve and how it will be measured. Good objectives are specific and tied to money or service: "reduce full stock-count time from 16 person-hours to 2", "cut dispatch errors from the current baseline by half", "complete...
• Also define the scope: which site, which items, which processes, and what is explicitly out of scope for phase one.
• Step 2 - Map the process
• Draw the current ("as-is") process step by step: who handles the item, where, with what document or system, and where errors and delays occur. Then design the future ("to-be") process with RFID.
• This is where many hidden issues surface: items that bypass the dock door, mixed pallets, returns, or staff who batch their work in ways the system did not expect.
• Step 3 - Site survey
MINDWARE

## Slide 4
Steps 1-3: Plan (cont.)
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• Visit every location where readers will operate. Measure dimensions, door widths, ceiling heights and travel speeds; note metal structures, racking, conveyors and machinery; check power and network availability and mounting options; and scan for existing RF...
MINDWARE

## Slide 5
Steps 4-6: Design and build
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• Step 4 - Tag selection and testing
• Shortlist tags suited to the items' materials, size, environment (heat, washing, chemicals, outdoor) and required read range. Then test them on real items : try several placements and orientations, test items as they will actually be packed and stacked, and...
• Watch out: A tag that reads well on a single item on a desk can fail inside a full carton or on a loaded pallet. Always test at the density and packaging you will use in production.
• Step 5 - Hardware design
• Choose the reader types for each read point - fixed readers, handhelds, printers, desktop readers - and design antenna count, placement, angles and power for each zone. Plan how operators will get feedback (lights, buzzers, screens), how equipment is mounted...
• Step 6 - Software and integration
• Define how raw reads become business events. Middleware or the application filters duplicates, applies rules (direction, zone, time window), and passes clean events to the ERP, WMS, MES or asset system through APIs, files or messages.
MINDWARE

## Slide 6
Steps 4-6: Design and build (cont.)
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• Pay particular attention to commissioning , the moment a tag is first linked to an item. If labels are printed and encoded in-house, decide who prints them, how each encoded EPC is verified by read-back, and how voided or damaged labels are handled; see RFID...
• Finally, decide what the users will actually see. Operators need simple, immediate feedback - a green light for a complete load, a red light and a list of missing items for an incomplete one.
MINDWARE

## Slide 7
Steps 7-9: Deploy and improve
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• Step 7 - Pilot with success criteria
• Run the complete solution - tags, hardware, software, integration and people - in a limited but realistic area, such as one store, one dock door or one department, for long enough to see normal variation (typically several weeks). Before starting, write down...
• Example: A distributor's pilot criterion was "at least the agreed target read rate for mixed cartons on pallets through Dock 3 at normal forklift speed, over four weeks, with every miss caught by the exception screen". Week one missed the target because...
• Step 8 - Rollout and training
• Roll out in phases, site by site or process by process, using a standard installation and configuration package derived from the pilot. Train every user group for its role: operators on daily use and exceptions, supervisors on reports, IT on support and...
• Step 9 - Support and continuous improvement
• After go-live, monitor reader health and read-rate trends, keep spares, and assign clear responsibility for first-line and vendor support. Review KPIs against the baseline monthly at first, then quarterly.
MINDWARE

## Slide 8
Roles in the RFID project team
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• Executive sponsor - Owns the business case, approves budget, removes obstacles.
• Project / process owner (operations) - Leads day to day, owns the to-be process, signs off pilot results.
• RFID engineer or integrator - Site survey, tag testing, hardware design, tuning.
• IT / integration lead - Middleware, ERP/WMS interfaces, network, security, data.
• Floor champions / key users - Represent operators, test the process, train colleagues.
• Finance - Baseline costs, ROI tracking, capex and opex planning.
• For small projects one person may hold several roles, and an external partner such as our RFID consulting team can cover the engineering and integration roles.
MINDWARE

## Slide 9
Example timeline
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• An illustrative timeline for a single-site warehouse project with two dock doors and handheld cycle counting. Durations are indicative and overlap in practice.
• 1-2 - Objectives, KPIs, baseline measurement - Signed scope and KPI sheet
• 2-4 - Process mapping and site survey - As-is / to-be maps, survey report
• 4-7 - Tag selection and testing - Approved tag and placement, test report
• 6-9 - Hardware design, procurement, integration build - Design document, tested interfaces
• 10-14 - Pilot at one dock door - Pilot report against success criteria
• 15-18 - Fixes, rollout to second door, training - Go-live, updated SOPs
MINDWARE

## Slide 10
Common reasons RFID projects fail
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• Technology first: buying hardware before defining the problem and KPIs.
• No baseline: benefits cannot be proven, so funding for rollout stalls.
• Lab testing only: tags tested on single items, not real packed loads.
• Integration underestimated: reads arrive but no business system uses them.
• Process unchanged: staff keep doing manual checks, so RFID adds cost without saving any.
• Poor master data: tags linked to wrong or duplicate records.
• Uncontrolled read zones: stray reads from neighbouring areas create false events.
MINDWARE

## Slide 11
Common reasons RFID projects fail (cont.)
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• No owner after go-live: performance degrades as layouts and products change.
• Tip: If you remember one thing, make it this: define success in numbers before the pilot starts, and do not scale up until the pilot meets them.
MINDWARE

## Slide 12
Printable implementation checklist
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
• 1 - Objectives written, KPIs defined, baseline measured, scope agreed - Sponsor / process owner
• 2 - As-is and to-be process maps approved; tagging level and exception handling decided - Process owner
• 3 - Site survey completed: dimensions, metal, RF scan, power, network, mounting - RFID engineer
• 4 - Tags tested on real items at production density; encoding scheme fixed - RFID engineer
• 5 - Reader, antenna and printer design documented; local band compliance confirmed - RFID engineer
• 6 - Data flow, business rules and interfaces built and tested; security and privacy reviewed - IT lead
• Next, work out the numbers in RFID cost and ROI . If you want to lead projects like this professionally, the Certified RFID Specialist Program covers each step hands-on.
MINDWARE

## Slide 13
Indian RFID - Mindware: from consultation to implementation
Indian RFID - Mindware | www.indianrfid.com | +91-9717122688 | gm@indianbarcode.com
1 Consultation
2 Site survey
3 Pilot
4 Supply
5 Encoding & software
6 Installation & training
7 Support & AMC
Mindware (New Delhi, since 1997) and its RFID division Indian RFID take your project from the first conversation to a working system - and support it after go-live.
Phone / WhatsApp: +91-9717122688 Email: gm@indianbarcode.com
S-4, Pankaj Plaza, Pocket-7, Plot-7, Dwarka Sector-12, New Delhi - 110078
www.indianrfid.com | Free guides: www.indianrfid.com/whitepapers
MINDWARE